## Staging Bug Report
# | Bug | Area | Severity | Root Cause | File(s) & Line(s) | Action Required | Effort
PII ENCRYPTION & DATA FLOW (Root cause: decrypt missing on memo/screening paths)
1 | Nationality shows "not provided" in compliance memo | Compliance Memo | P0 | ComplianceMemoHandler.post() reads directors/ubos from DB WITHOUT calling decrypt_pii_fields(). Nationality is Fernet-encrypted in DB, so memo_handler.py receives encrypted gibberish which fails .get() fallback to "nationality not provided". | server.py:2513-2514 memo_handler.py:317,323 PII_FIELDS: server.py:242-243 | Add decrypt_pii_fields() calls in ComplianceMemoHandler before passing to build_compliance_memo(). Pattern exists at server.py:711-714. | 30 min
2 | UBO ownership shows 0% everywhere | Compliance Memo Back Office | P0 | ownership_pct is in PII_FIELDS_UBOS and encrypted as a Fernet string. On read, it decrypts to string "50" not float 50. Memo handler does float(u.get("ownership_pct",0) or 0) which fails on encrypted string → 0. Back office shows 0% for same reason. | server.py:243 (PII_FIELDS_UBOS) server.py:2513-2514 memo_handler.py:93,111,115,119 | 1) Add decrypt in ComplianceMemoHandler (same fix as Bug 1). 2) After decrypt, cast ownership_pct to float. 3) ALSO: consider removing ownership_pct from PII_FIELDS_UBOS — a percentage is not PII. | 30 min
3 | Beneficial ownership "could not be verified" | Compliance Memo | P0 | Direct consequence of Bug 2. control_pct resolves to "0" because ownership_pct is encrypted. Line 384 condition control_pct in ("0") triggers "could not be verified" branch. With decryption fix, this auto-resolves. | memo_handler.py:93-95,119,384-386 | Same fix as Bug 2 — once ownership_pct decrypts correctly, control_pct will have the real value and the verified branch fires. | 0 min (fixed by Bug 2)
4 | Source of Funds / Expected Volume "not provided" in memo | Compliance Memo | P0 | memo_handler.py reads app.get("source_of_funds") and app.get("expected_volume") but these are NOT columns in the applications table — they are nested inside prescreening_data JSONB. ComplianceMemoHandler passes the raw app row dict, so these keys don't exist. | memo_handler.py:42-43 server.py:2505,2518 db.py (no source_of_funds column) | In ComplianceMemoHandler, parse prescreening_data JSON and merge into app dict before passing to build_compliance_memo(). E.g.: app["source_of_funds"] = prescreening.get("source_of_funds",""). | 30 min
DOCUMENT VERIFICATION & STORAGE
5 | AI document verification returns identical mock results for all docs | Portal Document Checks | P0 | Three possible causes, all leading to _mock_verify_document() returning hardcoded "all pass": (a) ANTHROPIC_API_KEY not set on staging, (b) CLAUDE_MOCK_MODE=true, (c) anthropic package not installed. Also: even when real AI runs, it only receives filename/type metadata — not the actual document bytes. | claude_client.py:489-520,558-594 server.py:1585-1597,1599-1616 | 1) Set ANTHROPIC_API_KEY in ECS env vars. 2) Ensure CLAUDE_MOCK_MODE is unset/false. 3) Long-term: send actual document file to Claude vision API in verify_document(). | 1 hr (env) + 4 hrs (vision)
6 | Back office cannot view/download client-uploaded documents | Back Office Documents | P0 | No DocumentDownloadHandler exists. Upload endpoint saves files to disk at uploads/documents/, but there is no GET endpoint to serve them. Additionally, AWS ECS has no persistent disk — files lost on container restart. | server.py:1414-1438 (upload) server.py:3870-3871 (routes, no download) No download handler exists | 1) Create DocumentDownloadHandler (GET /api/documents/:id/download) that reads file from UPLOAD_DIR and streams with correct MIME type. 2) Wire S3 for persistent storage on ECS. | 2 hrs + 4 hrs (S3)
SCREENING & AML
7 | Screening "View" button opens application page, not screening results | Back Office Screening | P1 | renderScreening() at line 3705 calls openAppDetail(app.ref) which navigates to the full application detail view. No dedicated screening results modal or page exists. | arie-backoffice.html:3693-3709 | Create a screening results modal/section that displays the screening_report from prescreening_data. Change View button to open that modal instead of openAppDetail(). | 4 hrs
8 | Screening status hardcoded to PEP flag, not actual completion | Back Office Screening | P1 | Line 3704 shows "Review" if isPEP else "Cleared" — this is based on PEP flag, not whether screening actually ran. No screening_status field exists in DB. ScreeningHandler stores results in prescreening_data but doesn't set a status flag. | arie-backoffice.html:3704 server.py:2074-2083 db.py (no screening_status column) | 1) Add screening_status column to applications table. 2) Update ScreeningHandler to set status on completion. 3) Update backoffice to read real status. | 3 hrs
DASHBOARD & REPORTS (Hardcoded UI)
9 | Onboarding Lanes shows zeros (or stale hardcoded numbers) | Dashboard | P1 | Lane counts at lines 793/797/801 are hardcoded HTML values (18/12/17). No JavaScript function calculates counts from APPLICATIONS array grouped by onboarding_lane field. | arie-backoffice.html:793,797,801 | Add JS in renderDashboardRecent() to count APPLICATIONS by lane and update the span elements dynamically. | 1 hr
10 | Reports page charts (Monthly Trend, Rejection Reasons) are 100% static | Reports | P1 | Charts at lines 1357-1376 are pure HTML with hardcoded bar heights and percentages. No API endpoint exists to fetch analytics data. No JS function updates these charts. | arie-backoffice.html:1357-1376 | 1) Create /api/analytics endpoint in server.py that aggregates application data by month and rejection reason. 2) Replace static HTML with JS-rendered charts from API data. | 6 hrs
API INTEGRATIONS
11 | Claude/Anthropic API missing from API Integration Status | Back Office Settings | P2 | APIStatusHandler response (server.py:2145-2174) lists Sumsub, OpenCorporates, IP Geo but omits Claude. Frontend apis array (arie-backoffice.html:7844) also missing it. | server.py:2145-2174 arie-backoffice.html:7840-7871 | Add anthropic_api entry to APIStatusHandler response checking ANTHROPIC_API_KEY. Add to frontend apis array. | 30 min
12 | Sumsub AML and OpenCorporates showing "SIMULATED" | Back Office Settings | P2 | These show SIMULATED because SUMSUB_APP_TOKEN / OPENCORPORATES_API_KEY env vars are not set on staging. The code correctly checks for these keys. | server.py:2145-2174 | Set SUMSUB_APP_TOKEN, SUMSUB_SECRET_KEY, and OPENCORPORATES_API_KEY in ECS env vars when ready to go live with these providers. | Config only
FEATURES NOT YET FUNCTIONAL (Expected — Roadmap Items)
13 | Regulatory Intelligence page is frontend-only with seed data | Reg Intel | P2 | Full UI exists with 2 seeded regulatory documents and AI analysis display. But no backend endpoints exist — all data is hardcoded in arie-backoffice.html:5904-6400. Upload/analyze function has no server-side handler. | arie-backoffice.html:5904-6400 No server.py endpoints | Phase 3 roadmap: Build /api/regulatory/* endpoints with Claude-powered analysis. Connect frontend upload to backend. Add regulatory document DB table. | 2–3 weeks
14 | AI Supervisor is rule-based only, not Claude-powered | Supervisor | P2 | supervisor_engine.py performs 11 deterministic contradiction checks but makes zero Claude API calls. The supervisor framework in supervisor/ directory has agent schemas but executors are not wired to Claude. | supervisor_engine.py:13-330 supervisor/schemas.py | Phase 3 roadmap: Wire supervisor agents to Claude for AI-powered review. Current rule-based approach works for MVP — AI enhancement is an upgrade, not a bug. | 1–2 weeks
SUMMARY: 6 P0 bugs (data integrity — must fix before live clients), 4 P1 bugs (UX/completeness), 4 P2 bugs (roadmap/config). Estimated total: ~3 days for P0, ~2 days for P1.